## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload knowledge-base documents so that I can query their content. | Must | Document extraction pipeline | Najla Fathima | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want documents in supported formats to be extracted and normalized for retrieval. | Must | Document upload | Team | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want document text split into meaningful chunks so retrieval can find relevant context. | Must | Extraction/cleaning | Team | Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want semantic embeddings stored in a vector database for knowledge retrieval. | Must | Chunking | Team | Completed
Sprint 2 | Sprint 2 | US-05 | As a user, I want my question understood before retrieval so relevant knowledge is searched. | Must | RAG pipeline | Team | Completed
Sprint 2 | Sprint 2 | US-06 | As a user, I want queries routed appropriately between retrieval, clarification and direct response paths. | Must | Query understanding | Team | Completed
Sprint 2 | Sprint 2 | US-07 | As a user, I want retrieved chunks reranked so the most relevant evidence is used. | Must | Vector retrieval | Team | Completed
Sprint 2 | Sprint 2 | US-08 | As a user, I want answers grounded in uploaded documents with source information. | Must | Retrieval + response generation | Team | Completed
Sprint 3 | Sprint 3 | US-09 | As a user, I want follow-up questions to retain conversation context. | Must | Conversation ID/memory | Najla Fathima | Completed
Sprint 3 | Sprint 3 | US-10 | As a user, I want clarification questions when my query is ambiguous or incomplete. | Must | Query understanding | Team | Completed
Sprint 3 | Sprint 3 | US-11 | As a user, I want voice input and spoken responses for easier interaction. | Should | Browser Speech APIs | Najla Fathima | Completed
Sprint 3 | Sprint 3 | US-12 | As a user, I want to inspect sources, chunks, relevance and citations behind an answer. | Must | Retrieval metadata | Najla Fathima | Completed
Sprint 4 | Sprint 4 | US-13 | As a user, I want to view query history and conversation statistics. | Should | Conversation API | Najla Fathima | Completed
Sprint 4 | Sprint 4 | US-14 | As a user, I want charts for query activity, conversation usage and confidence distribution. | Should | History dashboard | Najla Fathima | Completed
Sprint 4 | Sprint 4 | US-15 | As an administrator, I want analytics and knowledge-gap information to understand unanswered or low-confidence queries. | Should | Analytics service | Team | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | US-01-T01 | Review upload and document ingestion flow | TBD | TBD | Team | Analysis | Completed | 4 | Day 1: 4
US-01 | US-01-T02 | Implement/validate document upload handling | TBD | TBD | Team | Development | Completed | 8 | Day 2: 8
US-02 | US-02-T01 | Validate PDF/DOCX/image extraction paths | TBD | TBD | Team | Testing | Completed | 6 | Day 3: 6
US-03 | US-03-T01 | Clean extracted text and configure chunking | TBD | TBD | Team | Development | Completed | 8 | Day 4: 8
US-04 | US-04-T01 | Generate embeddings using all-MiniLM-L6-v2 | TBD | TBD | Team | AI/RAG | Completed | 6 | Day 5: 6
US-04 | US-04-T02 | Store and validate vectors in ChromaDB | TBD | TBD | Team | AI/RAG | Completed | 6 | Day 6: 6
US-03 | US-03-T02 | Test chunk boundaries and metadata preservation | TBD | TBD | Team | Testing | Completed | 5 | Day 7: 5
US-04 | US-04-T03 | Test semantic retrieval against uploaded content | TBD | TBD | Team | Testing | Completed | 6 | Day 8: 6
US-08 | US-08-T01 | Integration test ingestion-to-retrieval flow | TBD | TBD | Team | Testing | Completed | 6 | Day 9: 6
US-05 | US-05-T01 | Review query understanding workflow | TBD | TBD | Team | Analysis | Completed | 4 | Day 1: 4
US-05 | US-05-T02 | Implement query understanding integration | TBD | TBD | Team | Development | Completed | 8 | Day 2: 8
US-06 | US-06-T01 | Configure query routing for retrieval/clarification/general paths | TBD | TBD | Team | Development | Completed | 8 | Day 3: 8
US-07 | US-07-T01 | Validate hybrid retrieval and reranking signals | TBD | TBD | Team | AI/RAG | Completed | 8 | Day 4: 8
US-07 | US-07-T02 | Test relevance ordering for multiple candidate chunks | TBD | TBD | Team | Testing | Completed | 6 | Day 5: 6
US-08 | US-08-T02 | Integrate grounded response generation | TBD | TBD | Team | AI/RAG | Completed | 8 | Day 6: 8
US-08 | US-08-T03 | Validate source/citation mapping | TBD | TBD | Team | Testing | Completed | 5 | Day 7: 5
US-06 | US-06-T02 | Test ambiguous and general queries | TBD | TBD | Team | Testing | Completed | 5 | Day 8: 5
US-08 | US-08-T04 | End-to-end RAG workflow validation | TBD | TBD | Team | Testing | Completed | 8 | Day 9: 8
US-09 | US-09-T01 | Analyze conversation ID and memory flow | TBD | TBD | Najla Fathima | Frontend Analysis | Completed | 4 | Day 1: 4
US-09 | US-09-T02 | Integrate previous-turn display and conversation state | TBD | TBD | Najla Fathima | Frontend Development | Completed | 8 | Day 2: 8
US-09 | US-09-T03 | Implement New Conversation/Clear Conversation behavior | TBD | TBD | Najla Fathima | Frontend Development | Completed | 6 | Day 3: 6
US-12 | US-12-T01 | Build retrieval/source context inspector UI | TBD | TBD | Najla Fathima | Frontend Development | Completed | 8 | Day 4: 8
US-12 | US-12-T02 | Display relevance and semantic retrieval information | TBD | TBD | Najla Fathima | Frontend Development | Completed | 6 | Day 5: 6
US-11 | US-11-T01 | Implement Web Speech API voice input | TBD | TBD | Najla Fathima | Frontend Development | Completed | 8 | Day 6: 8
US-11 | US-11-T02 | Implement browser text-to-speech Read Aloud/Stop | TBD | TBD | Najla Fathima | Frontend Development | Completed | 6 | Day 7: 6
US-11 | US-11-T03 | Handle speech lifecycle, cancellation and UI states | TBD | TBD | Najla Fathima | Frontend Testing | Completed | 5 | Day 8: 5
US-09 | US-09-T04 | Regression and integration testing of chat flow | TBD | TBD | Najla Fathima | Testing | Completed | 8 | Day 9: 8
US-13 | US-13-T01 | Analyze conversation API and history data structure | TBD | TBD | Najla Fathima | Analysis | Completed | 4 | Day 1: 4
US-13 | US-13-T02 | Design History & Statistics dashboard | TBD | TBD | Najla Fathima | UI Design | Completed | 5 | Day 2: 5
US-13 | US-13-T03 | Implement query history list and conversation details | TBD | TBD | Najla Fathima | Frontend Development | Completed | 8 | Day 3: 8
US-13 | US-13-T04 | Implement statistics cards and recent-query metrics | TBD | TBD | Najla Fathima | Frontend Development | Completed | 6 | Day 4: 6
US-14 | US-14-T01 | Implement Query Activity Over Time chart | TBD | TBD | Najla Fathima | Frontend Development | Completed | 6 | Day 5: 6
US-14 | US-14-T02 | Implement Queries Per Conversation chart | TBD | TBD | Najla Fathima | Frontend Development | Completed | 5 | Day 6: 5
US-14 | US-14-T03 | Implement Confidence Distribution and Sources/Query metric | TBD | TBD | Najla Fathima | Frontend Development | Completed | 6 | Day 7: 6
US-13 | US-13-T05 | Responsive styling, null handling and edge-case testing | TBD | TBD | Najla Fathima | Testing | Completed | 6 | Day 8: 6
US-13 | US-13-T06 | Build, lint and regression validation | TBD | TBD | Najla Fathima | Testing | Completed | 5 | Day 9: 5
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Need to understand ingestion and extraction flow. | Reviewed document pipeline and assigned ingestion tasks.
Sprint 1 | Day 3 | Different document formats require separate extraction paths. | Validated extraction paths and normalized text.
Sprint 1 | Day 5 | Embedding/vector setup needed validation. | Tested all-MiniLM-L6-v2 embeddings and ChromaDB storage.
Sprint 2 | Day 2 | Query routing behavior needed clarification. | Reviewed routing conditions and tested retrieval/clarification paths.
Sprint 2 | Day 5 | Similar chunks can receive close retrieval scores. | Validated reranking using multiple relevance signals.
Sprint 2 | Day 8 | Source mapping needed end-to-end verification. | Tested citation and source/chunk mapping.
Sprint 3 | Day 6 | Browser speech support varies by browser. | Added speech-state handling and tested supported browser behavior.
Sprint 4 | Day 4 | History metrics should not imply all-time data when detailed calls are limited. | Displayed recent-conversation metrics and handled null values.
Sprint 4 | Day 9 | Need final regression check after analytics UI changes. | Ran build/lint and regression validation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | TBD | TBD | Team | Start early integration testing | Delay validation until the end of ingestion work | Keep document-format testing visible throughout the sprint | Added extraction and retrieval checks during development.
2 | Sprint 2 | TBD | TBD | Team | Test query types separately | Couple all query paths together | Keep reranking and source validation in the workflow | Added focused tests for retrieval, clarification and source mapping.
3 | Sprint 3 | TBD | TBD | Team | Handle UI states explicitly | Leave speech cancellation until final testing | Keep conversation and transparency features integrated | Added loading, listening, TTS and context-inspector state handling.
4 | Sprint 4 | TBD | TBD | Team | Validate analytics edge cases early | Assume missing confidence/source values are always present | Keep frontend changes isolated from backend | Handled null data, responsive UI, build/lint and regression checks.
5
6
7