## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Najla Fathima | 17-Sep-2026 | Assistant response did not always preserve the intended context when a follow-up query was sent. | Sprint 3 | Team | Functional | Validated conversation ID/history flow and corrected frontend request/state handling. | 17-Sep-2026 | Closed | Regression tested follow-up conversation flow.
2 | Najla Fathima | 17-Sep-2026 | Read Aloud could continue after starting a new query. | Sprint 3 | Najla Fathima | UI/Functional | Cancelled active speech before sending a new query and when clearing conversation. | 17-Sep-2026 | Closed | Speech lifecycle retested.
3 | Najla Fathima | 17-Sep-2026 | Voice input UI did not clearly reflect listening state. | Sprint 3 | Najla Fathima | UI | Added listening/loading state handling and verified Web Speech API events. | 17-Sep-2026 | Closed | Browser-dependent speech support documented.
4 | Najla Fathima | 17-Sep-2026 | Context inspector could show missing values when retrieval metadata was unavailable. | Sprint 3 | Najla Fathima | UI | Added safe fallback handling for missing metadata fields. | 17-Sep-2026 | Closed | No crash with missing metadata.
5 | Team | 17-Sep-2026 | Similar retrieved chunks were difficult to distinguish using semantic similarity alone. | Sprint 2 | Team | Logical | Validated reranking with semantic, keyword, lexical, synergy and evidence signals. | 17-Sep-2026 | Closed | Top-ranked chunks are passed to response generation.
6 | Team | 17-Sep-2026 | Ambiguous queries could proceed without enough context for a precise answer. | Sprint 2 | Team | Logical | Integrated clarification path in the query workflow. | 17-Sep-2026 | Closed | Clarification response tested.
7 | Team | 17-Sep-2026 | Source/chunk mapping required end-to-end validation. | Sprint 2 | Team | Functional | Verified document, page/chunk and citation mapping through retrieval and response flow. | 17-Sep-2026 | Closed | Source mapping regression passed.
8 | Team | 17-Sep-2026 | History page could request too many detailed conversation calls. | Sprint 4 | Najla Fathima | Performance | Limited detailed history fetches to the 20 most recently updated conversations. | 17-Sep-2026 | Closed | Dashboard now uses bounded detail retrieval.
9 | Najla Fathima | 17-Sep-2026 | History statistics could break when confidence or source values were null. | Sprint 4 | Najla Fathima | UI/Functional | Added null-safe metric calculations and fallback display values. | 17-Sep-2026 | Closed | Empty/null data tested.
10 | Najla Fathima | 17-Sep-2026 | Analytics charts needed to render without adding an external chart dependency. | Sprint 4 | Najla Fathima | UI | Implemented charts with native CSS/HTML visualization. | 17-Sep-2026 | Closed | Build completed without chart package dependency.
11 | Najla Fathima | 17-Sep-2026 | Frontend lint flagged a Hooks-related issue during History page development. | Sprint 4 | Najla Fathima | Standards | Moved hook usage to comply with Rules of Hooks and reran lint. | 17-Sep-2026 | Closed | Lint returned zero errors.
12 | Team | 17-Sep-2026 | Document formats have different extraction characteristics. | Sprint 1 | Team | Logical | Used format-specific extraction and OCR before common cleaning/chunking. | 17-Sep-2026 | Closed | PDF/DOCX/image processing paths validated.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others